## OKTCo
Code | FR Sheet Name (WS F&G) | PID | UID | Projected / Actual In-Service (mmm-yyyy) | Project & TP# | --- P R E V I O S L Y P U B L I S H E D --- | [15 empty] | --- P R E V I O S L Y P U B L I S H E D --- |  |  |  | --- P R E V I O S L Y P U B L I S H E D --- |  |  |  | --- P R E V I O S L Y P U B L I S H E D --- |  |  |  | --- P R E V I O S L Y P U B L I S H E D --- | [5 empty] | --- P R E V I O S L Y P U B L I S H E D --- | [5 empty] | --- P R E V I O S L Y P U B L I S H E D --- |  |  |  |  | --- WS-F and WS-G SUMMARY Input Data --- | [5 empty] | COMMENTS
[6 empty] | 09 Update | 2010 Update |  |  | 2011 Update |  |  |  | 2012 Update |  |  |  | 2013 Update |  |  |  | 2014 Update |  |  |  | 2015 Update |  |  |  | 2016 Update |  |  |  | 2017 Update | [5 empty] | 2018 Update | [5 empty] | 2019 Update |  |  |  |  | 2020 Update
[6 empty] | YE2009 Projected (8/31/09) << WS-F >> | YE2009 Actual << WS-G >> | YE2010 Projected << WS-F >> | YE09 to YE10 Variance | YE2010 Actual (May'11) << WS-G >> | YE2011 Projected (May '11) << WS-F >> | YE2010 Variance (Projected to Actual) | YE10 (actual) to YE11 (Projected) Variance | YE2011 Actual (May'12) << WS-G >> | YE2012 Projected (May '12) << WS-F >> | YE2011 Variance (Projected to Actual) | YE11 (actual) to YE12 (Projected) Variance | YE2012 Actual (May'13) << WS-G >> | YE2013 Projected (May '13) << WS-F >> | YE2012 Variance (Projected to Actual) | YE12 (actual) to YE13 (Projected) Variance | YE2013 Actual (May'14) << WS-G >> | YE2014 Projected (May '14) << WS-F >> | YE2013 Variance (Projected to Actual) | YE13 (actual) to YE14 (Projected) Variance | YE2014 Actual (May'15) << WS-G >> | YE2015 Projected (May '15) << WS-F >> | YE2014 Variance (Projected to Actual) | YE14 (actual) to YE15 (Projected) Variance | YE2015 Actual (May'16) << WS-G >> | YE2016 Projected (May '16) << WS-F >> | YE2015 Variance (Projected to Actual) | YE15 (actual) to YE16 (Projected) Variance | YE2016 Actual (May'17) << WS-G >> | YE2017 Projected (May '17) << WS-F >> | YE2017 Projected Adjusted (Oct '17) << WS-F >> | YE2018 Projected (Oct '17) << WS-F >> | YE2016 Variance (Projected to Actual) | YE16 (actual) to YE17 (Projected) Variance | YE2017 Actual (May '18) << WS-G >> | YE2018 Projected (May '18) << WS-F >> | YE2018 Projected Adjusted (Oct '18) << WS-F >> | YE2019 Projected (Oct '18) << WS-F >> | YE2017 Variance (Projected to Actual) | YE17 (Actual) to YE18 (Projected) Variance | YE2018 Actual (May '19) << WS-G >> | YE2019 Projected (Oct '19) << WS-F >> | YE2020 Projected (Oct '19) << WS-F >> | YE2018 Variance (Projected to Actual) | YE18 (Actual) to YE19 (Projected) Variance | YE2019 Actual (May '20) << WS-G >> | YE2020 Projected (May '2020) << WS-F >> | YE2020 Projected (Oct '20) << WS-F >> | YE2021 Projected (Oct '20) << WS-F >> | YE2019 Variance (Projected to Actual) | YE19 (Actual) to YE20 (Projected) Variance
t | OKT.001 | Total | Total | 2010-12-01 | Snyder 138 kv Terminal Addition (TP2009013) | --- | --- | 767749 | --- | 634790 | 634790 | -17.32% | 0% | 706495.57 | 706495.57 | 11.3% | 0% | 723818 | 723818 | 2.452% | 0% | 723818 | 723818 | 0% | 0% | 723818 | 723818 | 0% | 0% | 723818 | 723818 |  |  | 723818 | 723818 | 723818 | 723818 |  |  | 723818 | 723818 | 723818 | 723818 |  |  | 723818 | 723818 | 723818 |  |  | 723818 | 723818
c | OKT.001 | 480 | 10617 |  | Build new 4 mile AEP Snyder - WFEC Snyder 138 kV. WFEC to connect AEP Snyder to WFEC Snyder. AEP to provide 138 kV terminal at AEP Snyder. | [20 empty] | 723818 | 723818 |  |  | 723818 | 723818 |  |  | 723818 | 723818 | 723818 | 723818 |  |  | 723818 | 723818 | 723818 | 723818 |  |  | 723818 | 723818 | 723818 |  |  | 723818 | 723818
t | OKT.002 | Total | Total | 2010-06-01 | CoffeyvilleT to Dearing 138 kv Rebuild - 1.1 mi (TP2008013) | --- | --- | 1000000 | --- | 981860 | 981860 | -1.814% | 0% | 985777.34 | 985777.34 | 0.399% | 0% | 985777 | 985777 | -3.449e-05% | 0% | 985777 | 985777 | 0% | 0% | 985777.34 | 985777.34 | 3.449e-05% | 0% | 985777 | 985777 |  |  | 985777 | 985777 | 985777 | 985777 |  |  | 985777 | 985777 | 985777 | 985777 |  |  | 985777 | 985777 | 985777 |  |  | 985777 | 985777 |  |  |  |  | Also see related PSO project (P.013).
c | OKT.002 | 295 | 10381 |  | AEPW to reconductor 1.09 miles of 795 ACSR with 1590 ACSR. (Also, Westar to rebuild 3.93 miles of 795 ACSR with 1590 ACSR.) These ratings are just for the AEP facilities. | [20 empty] | 985777.34 | 985777.34 |  |  | 985777 | 985777 |  |  | 985777 | 985777 | 985777 | 985777 |  |  | 985777 | 985777 | 985777 | 985777 |  |  | 985777 | 985777 | 985777 |  |  | 985777 | 985777
t | OKT.003 | Total | Total | 2011-10-01 | Tulsa Power Station Reactor (TP2009090) | --- | --- | --- | --- | --- | 956000 | --- | --- | 614691 | 614691 | -35.7% | 0% | 614753 | 614753 | 0.01009% | 0% | 614753 | 614753 | 0% | 0% | 614752.9 | 614752.9 | -1.627e-05% | 0% | 614753 | 614753 |  |  | 614753 | 614753 | 614753 | 614753 |  |  | 614753 | 614753 | 614753 | 614753 |  |  | 614753 | 614753 | 614753 |  |  | 614753 | 614753
c | OKT.003 | 937 | 11237 |  | Install a 2% reactor at the Tulsa Power Station limiting flow on the Tulsa Power Station-Riverside 138 kV line. | [20 empty] | 614752.9 | 614752.9 |  |  | 614753 | 614753 |  |  | 614753 | 614753 | 614753 | 614753 |  |  | 614753 | 614753 | 614753 | 614753 |  |  | 614753 | 614753 | 614753 |  |  | 614753 | 614753
t | OKT.004 | Total | Total | 2011-06-01 | Bartlesville SE to Coffeyville T Rebuild (TP2008079-Transco) | --- | --- | --- | --- | --- | 12876000 | --- | --- | 11790024 | 11790024 | -8.434% | 0% | 11742800 | 11742800 | -0.4005% | 0% | 11742800 | 11742800 | 0% | 0% | 11742800 | 11742800 | 0% | 0% | 11742800 | 11742800 |  |  | 11742800 | 11742800 | 11742800 | 11742800 |  |  | 11742800 | 11742800 | 11742800 | 11742800 |  |  | 11742800 | 11742800 | 11742800 |  |  | 11742800 | 11742800 |  |  |  |  | Also see related PSO project (P.011).
c | OKT.004 | 446 | 10578 |  | Rebuild approximately 13 miles of line with 1590 ACSR to achieve a minimum 2000 Amp emergency rating | [20 empty] | 11742800 | 11742800 |  |  | 11742800 | 11742800 |  |  | 11742800 | 11742800 | 11742800 | 11742800 |  |  | 11742800 | 11742800 | 11742800 | 11742800 |  |  | 11742800 | 11742800 | 11742800 |  |  | 11742800 | 11742800
c | OKT.004 | 454 | 10588 |  | Included in 10578 | [20 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0
c | OKT.004 | 902 | 11199 |  | Included in 10578 | [20 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0
c | OKT.004 | 911 | 11208 |  | Included in 10578 | [20 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0
n/a | OKT.005 | Total | Total | 2012-04-01 | Install 345kV terminal at Valliant (TP2007167) | --- | --- | --- | --- | --- | --- | --- | --- | --- | 3951600 | --- | --- | 4377316 | 4377316 | 10.77% | 0% | [8 empty] | 0% |  |  |  | 0% | [22 empty] | Delete: Not a BPU…no longer reported for Sched 11 purposes.
n/a | OKT.005 | 288 | 10374 |  | Install 345 kV terminal equipment at Valliant substation. | [24 empty] | 0% |  |  |  | 0%
t | OKT.006 | Total | Total | 2013-08-01 | Canadian River - McAlester City 138 kV Line Conversion (TP2009095) | --- | --- | --- | --- | --- | --- | --- | --- | --- | 6627800 | --- | --- | 9966686 | 28567786 | 50.38% | 186.6% | 28682400 | 28682400 | 0.4012% | 0% | 28914235.74 | 28914235.74 | 0.8083% | 0% | 28914236 | 28914236 |  |  | 28914236 | 28914236 | 28914236 | 28914236 |  |  | 28914236 | 28914236 | 28914236 | 28914236 |  |  | 28914236 | 28914236 | 28914236 |  |  | 28914236 | 28914236 |  |  |  |  | Also see related PSO project (P.012). Multi-element multi-year base plan project. Final in-service yr in 12' and 13'.
c | OKT.006 | 767 | 11011 |  | Convert 17 mile Canadian River - McAlester City line from 69 kV to 138 kV. | [20 empty] | 28914235.74 | 28914235.74 |  |  | 28914236 | 28914236 |  |  | 28914236 | 28914236 | 28914236 | 28914236 |  |  | 28914236 | 28914236 | 28914236 | 28914236 |  |  | 28914236 | 28914236 | 28914236 |  |  | 28914236 | 28914236
c | OKT.006 | 767 | 11012 |  | Included in 11011 | [20 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0
c | OKT.006 | 767 | 11183 |  | Included in 11011 | [20 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0
c | OKT.006 | 767 | 11184 |  | Included in 11011 | [20 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0
t | OKT.007 | Total | Total | 2014-10-01 | Cornville Station Conversion (TP2011093) | [17 empty] | 10780000 |  |  | 10166784.78 | 10250000 | -5.688% | 0.8185% | 10218098.37 | 10218098.37 | -0.3112% | 0% | 10218098.37 | 10218098.37 | 10218098.37 | 10218098.37 | 0% | 0% | 10218098.37 | 10218098.37 | 10218098.37 | 10218098.37 | 0% | 0% | 10218098.37 | 10218098.37 | 10218098.37 | 0% | 0% | 10218098.37 | 10218098.37 |  |  | 0% | 0% | Also see related PSO project (P.016).
c | OKT.007 | 30346 | 50438 |  | Upgrade the Cornville 138 kV bus to breaker-and-a-half configuration in preparation for the 138 kV line conversion to Lindsay Water substation. | [20 empty] | 10166784.78 | 10250000 |  |  | 10218098.37 | 10218098.37 |  |  | 10218098.37 | 10218098.37 | 10218098.37 | 10218098.37 |  |  | 10218098.37 | 10218098.37 | 10218098.37 | 10218098.37 |  |  | 10218098.37 | 10218098.37 | 10218098.37 |  |  | 10218098.37 | 10218098.37
t | OKT.008 | Total | Total | 2014-06-01 | Coweta 69 kV Capacitor | --- | --- | --- | --- | [13 empty] | 669000 |  |  | 1864625.01 | 1864625.01 | 178.7% | 0% | 1864625 | 1864625 |  |  | 1864625 | 1864625 | 1864625 | 1864625 |  |  | 1864625 | 1864625 | 1864625 | 1864625 | 0% | 0% | 1864625 | 1864625 | 1864625 | 0% | 0% | 1864625 | 1864625 |  |  | 0% | 0%
c | OKT.008 | 30354 | 50405 |  | Install 6 Mvar capacitor at Coweta 69 kV. | [20 empty] | 1864625.01 | 1864625.01 |  |  | 1864625 | 1864625 |  |  | 1864625 | 1864625 | 1864625 | 1864625 |  |  | 1864625 | 1864625 | 1864625 | 1864625 |  |  | 1864625 | 1864625 | 1864625 |  |  | 1864625 | 1864625
t | OKT.009 | Total | Total | 2016-12-16 | Valliant-NW Texarkana 345 kV | --- | --- | --- | --- | [16 empty] | 0 | 2960000 |  |  | 2844116 | 3408237 | -3.915% | 19.83% | 67708596.12 | 69121596.12 | 69121596.12 | 69121596.12 | 1887% | 2.087% | 68230087.8 | 69121596.12 | 69121596.12 | 69121596.12 | -1.29% | 1.307% | 68247468.75 | 68247468.75 | 68247468.75 | -1.265% | 1.281% | 68247468.75 | 68247468.75 |  |  | 0% | 0% | 345 kV terminal work to be completed October 2015; Also see related PSO project (P.018) and SWEPCo project (S.058).
c | OKT.009 | 936 | 11236 |  | 345 kV from Valliant substation to NW Texarkana substation | [20 empty] | 0 | 2960000 |  |  | 2844116 | 3408237 |  |  | 67708596.12 | 69121596.12 | 69121596.12 | 69121596.12 |  |  | 68230087.8 | 69121596.12 | 69121596.12 | 69121596.12 |  |  | 68247468.75 | 68247468.75 | 68247468.75 |  |  | 68247468.75 | 68247468.75
t | OKT.011 | Total | Total | 2015-06-02 | Prattville-Bluebell 138 kV | --- | --- | --- | --- | [16 empty] | 0 | 7400000 |  |  | 8430000 | 8456490 | 13.92% | 0.3142% | 8535104 | 8535104 | 8535104 | 8535104 | 0.9296% | 0% | 8535104 | 8535104 | 8535104 | 8535104 | 0% | 0% | 8535104 | 8535104 | 8535104 | 0% | 0% | 8535104 | 8535104 |  |  | 0% | 0%
c | OKT.011 | 879 | 11158 |  | Rebuild 9.0 mile 138 kV line from Prattville to Bluebell with 1926.9 ACSR/TW | [20 empty] | 0 | 7400000 |  |  | 8430000 | 8456490 |  |  | 8535104 | 8535104 | 8535104 | 8535104 |  |  | 8535104 | 8535104 | 8535104 | 8535104 |  |  | 8535104 | 8535104 | 8535104 |  |  | 8535104 | 8535104
t | OKT.012 | Total | Total | 2013-12-01 | Wapanucka Customer Connection | --- | --- | --- | --- | [16 empty] | 7200873.82 | 7200873.82 |  | 0% | 7210308.95 | 7210308.95 |  |  | 7210308.95 | 7210308.95 | 7210308.95 | 7210308.95 |  |  | 7210308.95 | 7210308.95 | 7210308.95 | 7210308.95 | 0% | 0% | 7210308.95 | 7210308.95 | 7210308.95 | 0% | 0% | 7210308.95 | 7210308.95 |  |  | 0% | 0% | This was originally a customer-service project, then later became a BP project. Associated BPIDs P1214101, P12141005, and P12141009.
c | OKT.012 | 30750 | 51017 |  | Construct Wapanucka 138 kV station and Pontotoc-Wapanucka 138 kV line. | [20 empty] | 7200873.82 | 7200873.82 |  |  | 7210308.95 | 7210308.95 |  |  | 7210308.95 | 7210308.95 | 7210308.95 | 7210308.95 |  |  | 7210308.95 | 7210308.95 | 7210308.95 | 7210308.95 |  |  | 7210308.95 | 7210308.95 | 7210308.95 |  |  | 7210308.95 | 7210308.95
t | OKT.013 | Total | Total | 2015-11-05 | Grady Customer Connection | --- | --- | --- | --- | [16 empty] | 9011154 | 19043679.66 |  | 111.3% | 19988643 | 20178014 | 4.962% | 0.9474% | 20242007 | 20248060 | 20248060 | 20248060 | 0.3171% | 0.0299% | 20242585.05 | 20248060 | 20248060 | 20248060 | -0.02704% | 0.02705% | 20242585.05 | 20248060 | 20248060 | -0.02704% | 0.02705% | 20242585.05 | 20242585.05 |  |  | -0.02704% | 0% | This was originally a customer-service project, then later became a BP project. Also see related PSO project (P.020).
c | OKT.013 | 30748 | 51015 |  | Construct Grady 138 kV station and Grady-Lindsay Waterflood 138 kV line. | [20 empty] | 9011154 | 9389223.66 |  |  | 13235135 | 13165263 |  |  | 13308060 | 13308060 | 13308060 | 13308060 |  |  | 13308077.75 | 13308060 | 13308060 | 13308060 |  |  | 13308077.75 | 13308060 | 13308060 |  |  | 13308077.75 | 13308077.75 |  |  |  |  | In-serviced Nov-14
c | OKT.013 | 30747 | 51014 |  | Construct Round Creek 138 kV station and Round Creek-Grady 138 kV line. | [20 empty] | 0 | 9654456 |  |  | 6753508 | 7012751 |  |  | 6933947 | 6940000 | 6940000 | 6940000 |  |  | 6934507.3 | 6940000 | 6940000 | 6940000 |  |  | 6934507.3 | 6940000 | 6940000 |  |  | 6934507.3 | 6934507.3 |  |  |  |  | Trailing charges due to being in-service in Dec 2015
t | OKT.014 | Total | Total | 2014-04-01 | Darlington-Red Rock 138 kV line | --- | --- | --- | --- | [16 empty] | 13254470.19 | 13254470.19 |  | 0% | 13254470 | 13254470 |  |  | 13254470 | 13254470 | 13254470 | 13254470 |  |  | 13254470 | 13254470 | 13254470 | 13254470 | 0% | 0% | 13254470 | 13254470 | 13254470 | 0% | 0% | 13254470 | 13254470 |  |  | 0% | 0% | Also see related PSO project (P.021).
c | OKT.014 | 30746 | 51013 |  | Construct new 8-mile 138 kV line from Red Rock to Darlington. | [20 empty] | 13254470.19 | 13254470.19 |  |  | 13254470 | 13254470 |  |  | 13254470 | 13254470 | 13254470 | 13254470 |  |  | 13254470 | 13254470 | 13254470 | 13254470 |  |  | 13254470 | 13254470 | 13254470 |  |  | 13254470 | 13254470 |  |  |  |  | Cost includes all terminal work also.
t | OKT.015 | Total | Total | 2013-10-01 | Ellis 138 kV | --- | --- | --- | --- | [16 empty] | 4086696.07 | 4086696.07 |  | 0% | 4086696 | 4086696 |  |  | 4800037.86 | 0 | 0 | 0 |  |  | 4817114 | 0 | 0 | 0 | 0% | -100% | 4817114 | 0 | 0 | #DIV/0! | -100% | 4817114 | 4817114 |  |  | #DIV/0! | 0%
c | OKT.015 | 30770 | 51047 |  | Tap existing 138 kV line from Elk City to Red Hills Wind to construct new Ellis substation. | [20 empty] | 4086696.07 | 4086696.07 |  |  | 4086696 | 4086696 |  |  | 4800037.86 | 0 | 0 | 0 |  |  | 4817114 | 0 | 0 | 0 |  |  | 4817114 | 0 | 0 |  |  | 4817114 | 4817114 |  |  |  |  | OKTCo is constructing the rest of this project and when done will sell it to WFEC. It is part of a settlement with WFEC. We won't be able to get any cost recovery as it won't be our asset once sold to WFEC. I just opened the old project up for new WOs and the PM has put in IR $1,222,501.00
t | OKT.016 | Total | Total | 2017-06-29 | Darlington-Roman Nose 138 kV | --- | --- | --- | --- | [16 empty] | 0 | 0 |  | 0% | 0 | 0 |  |  | 0 | 10615000 | 10615000 | 10615000 |  |  | 11033622.83 | 10615000 | 10615000 | 10615000 | 3.944% | -3.794% | 11056565.36 | 11056565.36 | 11056565.36 | 4.16% | -3.994% | 11056565.36 | 11056565.36 |  |  | 0% | 0%
c | OKT.016 | 30619 | 50802 |  | Darlington-Roman Nose 138 kV - Construct 13.5 miles of new line. | [20 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 10615000 | 10615000 | 10615000 |  |  | 11033622.83 | 10615000 | 10615000 | 10615000 |  |  | 11056565.36 | 11056565.36 | 11056565.36 |  |  | 11056565.36 | 11056565.36 |  |  |  |  | Also see related PSO project (P.023).
t | OKT.017 | Total | Total | 2017-07-06 | Carnegie South-Southwestern 138 kV Line Rebuild | --- | --- | --- | --- | [16 empty] | 0 | 0 |  | 0% | 0 | 0 |  |  | 0 | 8899000 | 8899000 | 8899000 |  |  | 9557910 | 8899000 | 8899000 | 8899000 | 7.404% | -6.894% | 9589270.28 | 9657270.28 | 9657270.28 | 7.757% | -7.198% | 9589270.28 | 9589270.28 |  |  | -0.7041% | 0%
c | OKT.017 | 30873 | 51187 |  | Carnegie South-Southwestern 138 kV Line - Rebuild 15.6 miles and replace switch | [20 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 8899000 | 8899000 | 8899000 |  |  | 9557910 | 8899000 | 8899000 | 8899000 |  |  | 9589270.28 | 9657270.28 | 9657270.28 |  |  | 9589270.28 | 9589270.28
t | OKT.018 | Total | Total | 2017-12-07 | Chisholm - Gracemont 345 kV | --- | --- | --- | --- | [16 empty] | 0 | 0 |  | 0% | 0 | 0 |  |  | 0 | 82823000 | 82823000 | 82823000 |  |  | 87396515 | 82823000 | 82823000 | 82823000 | 5.522% | -5.233% | 88257196.21 | 88257196.21 | 88257196.21 | 6.561% | -6.157% | 87569395.13 | 87569395.13 |  |  | -0.7793% | 0%
c | OKT.018 | 30361 | 50413 |  | Chisholm - Gracemont 345 kV Line | [20 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 64868000 | 64868000 | 64868000 |  |  | 67454138 | 64868000 | 64868000 | 64868000 |  |  | 68693056.23 | 68693056.23 | 68693056.23 |  |  | 68004781.65 | 68004781.65
c | OKT.018 | 30361 | 50414 |  | Chisholm 345/230 kV Station | [20 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 16278000 | 16278000 | 16278000 |  |  | 18729195 | 16278000 | 16278000 | 16278000 |  |  | 18337760.15 | 18337760.15 | 18337760.15 |  |  | 18338233.65 | 18338233.65
c | OKT.018 | 30361 | 50768 |  | Chisholm 230 kV Line | [20 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 1677000 | 1677000 | 1677000 |  |  | 1213182 | 1677000 | 1677000 | 1677000 |  |  | 1226379.83 | 1226379.83 | 1226379.83 |  |  | 1226379.83 | 1226379.83
t | OKT.019 | Total | Total | 2018-12-21 | Fort Towson-Valliant 69 kV Line Rebuild | --- | --- | --- | --- | [16 empty] | 0 | 0 |  | 0% | 0 | 0 |  |  | 0 | 0 | 0 | 14897000 |  |  | 0 | 14897000 | 22387000 | 22387000 | 0% | 0% | 15689737.6 | 15833737.6 | 15833737.6 | -29.92% | 42.69% | 17124157 | 17124157 |  |  | 8.15% | 0% | Refer to related PSO project P.026. Estimates from improvement requisition; do not include Hugo line work (do not include P15204008)
c | OKT.019 | 31058 | 51562 |  | Fort Towson-Valliant 69 kV Line Rebuild | [20 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 14897000 |  |  | 0 | 14897000 | 22387000 | 22387000 |  |  | 15689737.6 | 15833737.6 | 15833737.6 |  |  | 17124157 | 17124157
c | OKT.019 | 31058 | 51561 |  | included above | [20 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0
t | OKT.020 | Total | Total | 2018-05-04 | Duncan-Comanche Tap 69 kV Rebuild and Duncan station upgrades | [28 empty] | 8338595.45 | 0 | 8591402.45 | 8591402.45 |  |  | 8789790.23 | 8591402.45 | 8591402.45 | 8591402.45 | 2.309% | -2.257% | 8934664.39 | 8934664.39 | 8934664.39 | 3.995% | -3.842% | 8934664.39 | 8934664.39 |  |  | 0% | 0% | Refer to related PSO project P.027. Line rebuild is in the TransCo line rehab program, b/c the NTC came after the program was approved. A11012089, A11012200, A11012077, A11012447, A13004055 are possible BPIDs for the line. Duncan station work was done under TP-2015-191.
c | OKT.020 | 31009 | 51454 |  | Duncan-Tosco Rebuild and Duncan station upgrades | [28 empty] | 0 | 0 | 8591402.45 | 8591402.45 |  |  | 8789790.23 | 8591402.45 | 8591402.45 | 8591402.45 |  |  | 8934664.39 | 8934664.39 | 8934664.39 |  |  | 8934664.39 | 8934664.39 |  |  |  |  | Line rebuild is in the TransCo line rehab program, b/c the NTC came after the program was approved.
c | OKT.020 | 31039 | 51524 |  | Comanche Tap-Tosco 69 kV Rebuild (included above) | [28 empty] | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 |  |  |  |  | Line rebuild is in the TransCo line rehab program, b/c the NTC came after the program was approved. Included in UID 51454.
t | OKT.021 | Total | Total | 2020-06-01 | Keystone Dam - Wekiwa 138 kV | [34 empty] | --- | --- | --- | --- | 0% | 0% | --- | 1282000 | 3543000 | 0% | 0% | --- | --- |  |  | 0% | #VALUE! | Includes line work, ROW and TFC, see PSO for Wekiwa station work. Note, for this update, ROW was forecast on PSO instead of OKT. (Manually moved the ROW to OKT.)
c | OKT.021 | 30809 | 51096 |  | Keystone Dam - Wekiwa 138 kV | [34 empty] | --- | --- | --- | --- |  |  | --- | 1282000 | 3543000 |  |  | --- | ---
NOTES:
< | Not above SPP $100,000 BP threshold.
New | New to BP list
c | AEP project component (components sum up to project total)
t | AEP project total
n/a | informational only; not included in calculations
Matched Last Year
Does Not Match Last Year, Needs Updating
Changed from Last Year, Updated