## PSO
Code | FR Sheet Name (WS F&G) | Projected / Actual In-Service (mmm-yyyy) | Project & TP# | - - - P R E V I O U S L Y P U B L I S H E D - - - | [17 empty] | --- P R E V I O S L Y P U B L I S H E D --- |  |  |  | --- P R E V I O S L Y P U B L I S H E D --- |  |  |  | --- P R E V I O S L Y P U B L I S H E D --- | [5 empty] | --- P R E V I O S L Y P U B L I S H E D --- | [5 empty] | --- P R E V I O S L Y P U B L I S H E D --- |  |  |  |  | --- WS-F and WS-G SUMMARY Input Data --- | [5 empty] | COMMENTS
|  |  |  | 09 Update | 2010 "Corrected" Update |  |  | 2011 "Corrected" Update |  |  | 2012 Update |  |  | 2013 Update |  |  |  | 2014 Update |  |  |  | 2015 Update |  |  |  | 2016 Update |  |  |  | 2017 Update | [5 empty] | 2018 Update | [5 empty] | 2019 Update |  |  |  |  | 2020 Update
|  |  |  | YE2009 Projected (8/31/09) << WS-F >> | YE2009 Actual (3/29/11)* << WS-G >> | YE2010 Projected (3/29/11) << WS-F >> | YE09 to YE10 (Projected) Variance | YE2010 Actual (12/21/11)* << WS-G >> | YE2011 Projected (12/21/11) << WS-F >> | YE10 to YE11 (Projected) Variance | YE2011 Actual (May'12) << WS-G >> | YE2012 Projected (May '12) << WS-F >> | YE11 to YE12 (Projected) Variance | YE2012 Actual (May'13) << WS-G >> | YE2013 Projected (May '13) << WS-F >> | YE2012 Variance (Projected to Actual) | YE12 (actual) to YE13 (Projected) Variance | YE2013 Actual (May'14) << WS-G >> | YE2014 Projected (May '14) << WS-F >> | YE2013 Variance (Projected to Actual) | YE13 (actual) to YE14 (Projected) Variance | YE2014 Actual (May'15) << WS-G >> | YE2015 Projected (May '15) << WS-F >> | YE2014 Variance (Projected to Actual) | YE14 (actual) to YE15 (Projected) Variance | YE2015 Actual (May'16) << WS-G >> | YE2016 Projected (May '16) << WS-F >> | YE2015 Variance (Projected to Actual) | YE15 (actual) to YE16 (Projected) Variance | YE2016 Actual (May'17) << WS-G >> | YE2017 Projected (May '17) << WS-F >> | YE2017 Projected Adjusted (Oct '17) << WS-F >> | YE2018 Projected (Oct '17) << WS-F >> | YE2016 Variance (Projected to Actual) | YE16 (Actual) to YE17 (Projected) Variance | YE2017 Actual (May '18) << WS-G >> | YE2018 Projected (May '18) << WS-F >> | YE2018 Projected Adjusted (Oct '18) << WS-F >> | YE2019 Projected (Oct '18) << WS-F >> | YE2017 Variance (Projected to Actual) | YE17 (Actual) to YE18 (Projected) Variance | YE2018 Actual (May '19) << WS-G >> | YE2019 Projected (Oct '19) << WS-F >> | YE2020 Projected (Oct '19) << WS-F >> | YE2018 Variance (Projected to Actual) | YE18 (Actual) to YE19 (Projected) Variance | YE2019 Actual (May '20) << WS-G >> | YE2020 Projected (May '2020) << WS-F >> | YE2020 Projected (Oct '20) << WS-F >> | YE2021 Projected (Oct '20) << WS-F >> | YE2019 Variance (Projected to Actual) | YE19 (Actual) to YE20 (Projected) Variance
| P.001 | 2009-06-01 | Riverside-Glenpool (TP2006087) | 579098 | 893857.87 | 893857.87 | 54.35% | 893857.87 | 893857.87 | 0% | 893857.87 | 893857.87 | 0% | 893857.87 | 893857.87 | 0% | 0% | 893857.87 | 893857.87 | 0% | 0% | 893858 | 893858 | 1.454e-05% | 0% | 893858 | 893858 | 0% | 0% | 893858 | 893858 | 893858 | 893858 | 0% | 0% | 893858 | 893858 | 893858 | 893858 | 0% | 0% | 893858 | 893858 | 893858 | 0% | 0% | 893858 | 893858 |  |  | 0% | 0%
| P.002 | 2009-05-01 | Craig Jct-Broken Bow (TP2007059) | 6704177 | 4725391.05 | 4725391.05 | -29.52% | 4688896 | 4688896 | 0.7783% | 4688896 | 4688896 | 0% | 4688896 | 4688896 | 0% | 0% | 4688896 | 4688896 | 0% | 0% | 4688896 | 4688896 | 0% | 0% | 4688896 | 4688896 | 0% | 0% | 4688896 | 4688896 | 4688896 | 4688896 | 0% | 0% | 4688896 | 4688896 | 4688896 | 4688896 | 0% | 0% | 4688896 | 4688896 | 4688896 | 0% | 0% | 4688896 | 4688896 |  |  | 0% | 0%
| P.003 | 2009-10-01 | WFEC new ties (TP2006054) | 9403820 | 8830340 | 12266531 | 30.44% | 12232148 | 12232148 | 0.2811% | 12232148 | 12232148 | 0% | 12232148 | 12232148 | 0% | 0% | 12232148 | 12232148 | 0% | 0% | 11456065 | 11456065 | -6.345% | 0% | 11456065 | 11456065 | 0% | 0% | 11456065 | 11456065 | 11456065 | 11456065 | 0% | 0% | 11456065 | 11456065 | 11456065 | 11456065 | 0% | 0% | 11456065 | 11456065 | 11456065 | 0% | 0% | 11456065 | 11456065 |  |  | 0% | 0%
| P.004 | 2008-07-01 | Cache-Snyder (TP2004147) | 14544152 | 14683511.33 | 14686911.33 | 0.02248% | 14615636 | 14615636 | 0.4877% | 14615636 | 14615636 | 0% | 14615636 | 14615636 | 0% | 0% | 14615636 | 14615636 | 0% | 0% | 14615636 | 14615636 | 0% | 0% | 14615636 | 14615636 | 0% | 0% | 14615636 | 14615636 | 14615636 | 14615636 | 0% | 0% | 14615636 | 14615636 | 14615636 | 14615636 | 0% | 0% | 14615636 | 14615636 | 14615636 | 0% | 0% | 14615636 | 14615636 |  |  | 0% | 0% | Includes new line and new terminals at both ends.
| P.005 | 2006-05-01 | Catoosa 138 kV Device | 387742 | 387742 | 387742 | 0.02248% | 387742 | 387742 | 0% | 387742 | 387742 | 0% | 387742 | 387742 | 0% | 0% | 387742 | 387742 | 0% | 0% | 387742 | 387742 | 0% | 0% | 387742 | 387742 | 0% | 0% | 387742 | 387742 | 387742 | 387742 | 0% | 0% | 387742 | 387742 | 387742 | 387742 | 0% | 0% | 387742 | 387742 | 387742 | 0% | 0% | 387742 | 387742 |  |  | 0% | 0%
| P.006 | 2008-04-01 | Pryor Jct 138/60 Upgrade autoxfmr (TP2006090) | 1520473 | 1520502 | 1520502 | 0.02248% | 1520502 | 1520502 | 0% | 1520502 | 1520502 | 0% | 1520502 | 1520502 | 0% | 0% | 1520502 | 1520502 | 0% | 0% | 1520502 | 1520502 | 0% | 0% | 1520502 | 1520502 | 0% | 0% | 1520502 | 1520502 | 1520502 | 1520502 | 0% | 0% | 1520502 | 1520502 | 1520502 | 1520502 | 0% | 0% | 1520502 | 1520502 | 1520502 | 0% | 0% | 1520502 | 1520502 |  |  | 0% | 0%
| P.007 | 2007-12-01 | Elk City-Elk City 69 CT upgrades (TP2007015) | 84424 | 84424 | 84424 | 0.02248% | 84424 | 84424 | 0% | 84424 | 84424 | 0% | 84424 | 84424 | 0% | 0% | 84424 | 84424 | 0% | 0% | 84424 | 84424 | 0% | 0% | 84424 | 84424 | 0% | 0% | 84424 | 84424 | 84424 | 84424 | 0% | 0% | 84424 | 84424 | 84424 | 84424 | 0% | 0% | 84424 | 84424 | 84424 | 0% | 0% | 84424 | 84424 |  |  | 0% | 0% | Not over $100K threshold for regional allocation.
| P.008 | 2006-03-01 | Weleetka & Okmulgee wavetrap r&r 81-805 (TP2005046) | 56133 | 56133 | 56133 | 0.02248% | 56133 | 56133 | 0% | 56133 | 56133 | 0% | 56133 | 56133 | 0% | 0% | 56133 | 56133 | 0% | 0% | 56133 | 56133 | 0% | 0% | 56133 | 56133 | 0% | 0% | 56133 | 56133 | 56133 | 56133 | 0% | 0% | 56133 | 56133 | 56133 | 56133 | 0% | 0% | 56133 | 56133 | 56133 | 0% | 0% | 56133 | 56133 |  |  | 0% | 0% | Not over $100K threshold for regional allocation.
| P.009 | 2007-04-01 | Tulsa SE r&r switches (TP2004033) | 72551 | 72551 | 72551 | 0.02248% | 72551 | 72551 | 0% | 72551 | 72551 | 0% | 72551 | 72551 | 0% | 0% | 72551 | 72551 | 0% | 0% | 72551 | 72551 | 0% | 0% | 72551 | 72551 | 0% | 0% | 72551 | 72551 | 72551 | 72551 | 0% | 0% | 72551 | 72551 | 72551 | 72551 | 0% | 0% | 72551 | 72551 | 72551 | 0% | 0% | 72551 | 72551 |  |  | 0% | 0% | Not over $100K threshold for regional allocation.
| P.010 | 2010-06-01 | Clinton City-Foss 69 wavetrap r&r (TP2009011) | n/a | n/a | 135400 | n/a | 96566 | 96566 | 40.21% | 96566 | 96566 | 0% | 96566 | 96566 | 0% | 0% | 96566 | 96566 | 0% | 0% | 96566 | 96566 | 0% | 0% | 96566 | 96566 | 0% | 0% | 96566 | 96566 | 96566 | 96566 | 0% | 0% | 96566 | 96566 | 96566 | 96566 | 0% | 0% | 96566 | 96566 | 96566 | 0% | 0% | 96566 | 96566 |  |  | 0% | 0% | Not over $100K threshold for regional allocation.
| P.011 | 2011-06-01 | Bartlesville SE to Coffeyville T Rebuild (TP2008079-PSO) | --- | --- | --- | --- | --- | 1624000 | --- | 1436737 | 1436737 | 13.03% | 1493723 | 1493723 | 3.966% | 0% | 1493723 | 1493723 | 0% | 0% | 1493723 | 1493723 | 0% | 0% | 1493723 | 1493723 | 0% | 0% | 1493723 | 1493723 | 1493723 | 1493723 | 0% | 0% | 1493723 | 1493723 | 1493723 | 1493723 | 0% | 0% | 1493723 | 1493723 | 1493723 | 0% | 0% | 1493723 | 1493723 |  |  | 0% | 0% | Also see related OKTransco project (OKT.004).
| P.012 | 2013-08-01 | Canadian River - McAlester City 138 kV Line Conversion (TP2009095) | --- | --- | --- | --- | --- | --- | --- | --- | 1132400 | --- | 504034 | 2750034 | -55.49% | 445.6% | 3242134 | 3242134 | 17.89% | 0% | 3305767.14 | 3305767.14 | 1.963% | 0% | 3305767 | 3305767 | 0% | 0% | 3305767 | 3305767 | 3305767 | 3305767 | 0% | 0% | 3305767 | 3305767 | 3305767 | 3305767 | 0% | 0% | 3305767 | 3305767 | 3305767 | 0% | 0% | 3305767 | 3305767 |  |  | 0% | 0% | Also see related OKTransco project (OKT.006). Multi-element multi-year base plan project. Final in-service yr in 12' and 13'.
| P.013 | 2010-06-01 | CoffeyvilleT to Dearing 138 kv Rebuild - 1.1 mi (TP2008013) | --- | --- | --- | --- | --- | --- | --- | 22097 | 22097 | --- | 22097 | 22097 | 0% | 0% | 22097 | 22097 | 0% | 0% | 22097 | 22097 | 0% | 0% | 22097 | 22097 | 0% | 0% | 22097 | 22097 | 22097 | 22097 | 0% | 0% | 22097 | 22097 | 22097 | 22097 | 0% | 0% | 22097 | 22097 | 22097 | 0% | 0% | 22097 | 22097 |  |  | 0% | 0% | Also see related OKTransco project (OKT.002). Total project expenditure is over $100k.
| P.014 | 2013-02-01 | Ashdown West - Craig Junction 138KV Rebuild (TP2009092) | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | n/a | 5562500 | --- | --- | 1035333 | 1035333 | -81.39% | 0% | 1035552 | 1035552 | 0.02115% | 0% | 1035552 | 1035552 | 0% | 0% | 1035552 | 1035552 | 1035552 | 1035552 | 0% | 0% | 1035552 | 1035552 | 1035552 | 1035552 | 0% | 0% | 1035552 | 1035552 | 1035552 | 0% | 0% | 1035552 | 1035552 |  |  | 0% | 0% | Asset transfer to SWEPCO completed. Only a portion of the project was transferred.
| P.015 | 2014-02-01 | Locust Grove to Lone Star 115 kV Rebuild 2.1 miles (TP2009093) | [14 empty] | n/a | 2295000 |  |  | 2246628.57 | 2246628.57 | -2.108% | 0% | 2246629 | 2246629 | 1.914e-05% | 0% | 2246629 | 2246629 | 2246629 | 2246629 | 0% | 0% | 2246629 | 2246629 | 2246629 | 2246629 | 0% | 0% | 2246629 | 2246629 | 2246629 | 0% | 0% | 2246629 | 2246629 |  |  | 0% | 0%
| P.016 | 2014-12-01 | Cornville Station Conversion (TP2011093) | [14 empty] | n/a | 5300000 |  |  | 4980780.16 | 5300000 | -6.023% | 6.409% | 5059196 | 5059196 | -4.543% | 0% | 5059278.04 | 5059278.04 | 5059278.04 | 5059278.04 | 0.001622% | 0% | 5059278.04 | 5059278.04 | 5059278.04 | 5059278.04 | 0% | 0% | 5059278.04 | 5059278.04 | 5059278.04 | 0% | 0% | 5059278.04 | 5059278.04 |  |  | 0% | 0% | Also see related OKTransco project (OKT.007).
| P.018 | 2017-03-01 | Valliant-NW Texarkana 345 kV | [14 empty] | n/a | 0 |  |  | 0 | 1500000 |  |  | 1338801 | 1338801 | -10.75% | 0% | 1338977.91 | 1338977.91 | 1338977.91 | 1338977.91 | 0.01321% | 0% | 1338977.91 | 1338977.91 | 1338977.91 | 1338977.91 | 0% | 0% | 1338977.91 | 1338977.91 | 1338977.91 | 0% | 0% | 1338977.91 | 1338977.91 |  |  | 0% | 0% | 345 kV line relocation to be completed November 2015; Also see related SWEPCo project (S.058) and OKTCo project (OKT.009).Need to Update the ISD to 2017
| P.020 | 2015-12-01 | Grady Customer Connection | [18 empty] | 0 | 1500000 |  |  | 1625288 | 1777912 | 8.353% | 9.391% | 1692023.17 | 1692023.17 | 1692023.17 | 1692023.17 | -4.831% | 0% | 1692023.17 | 1692023.17 | 1692023.17 | 1692023.17 | 0% | 0% | 1692023.17 | 1692023.17 | 1692023.17 | 0% | 0% | 1692023.17 | 1692023.17 |  |  | 0% | 0% | Also see related OKTransco project (OKT.013).
| P.021 | 2014-04-01 | Darlington-Red Rock 138 kV line | [18 empty] | 1725646.85 | 1725646.85 |  |  | 1725647 | 1725647 | 8.692e-06% | 0% | 1725647 | 1725647 | 1725647 | 1725647 | 0% | 0% | 1725647 | 1725647 | 1725647 | 1725647 | 0% | 0% | 1725647 | 1725647 | 1725647 | 0% | 0% | 1725647 | 1725647 |  |  | 0% | 0% | Also see related OKTransco project (OKT.014).
| P.022 | 2018-12-19 | Sayre 138 kV Capacitor Bank Addition | [18 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 483000 | 0 | 1140000 |  |  | 0 | 1140000 | 1140000 | 1140000 | 0% | 0% | 1919728.93 | 1919728.93 | 1919728.93 | 68.4% | -40.62% | 1961220.71 | 1961220.71 |  |  | 2.161% | 0% | ISD moved out to 2018.
| P.023 | 2017-06-29 | Darlington-Roman Nose 138 kV | [18 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 262000 | 262000 | 262000 |  |  | 330824.19 | 262000 | 262000 | 262000 | 26.27% | -20.8% | 330872.36 | 330872.36 | 330872.36 | 26.29% | -20.82% | 330872.36 | 330872.36 |  |  | 0% | 0% | Also see related OKTransco project (OKT.016).
| P.024 | 2018-06-01 | Northeastern Station 138 kV Terminal Upgrades | [18 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 244000 | 244000 |  |  | 244000 | 244000 | 244000 | 244000 | 0% | 0% | 244000 | 244000 | 244000 | 0% | 0% | 244000 | 244000 |  |  | 0% | 0% | This project was slated for 06/2017, however, the metering CT failed, and was replaced by TFS in 05/2016.
| P.025 | 2018-05-25 | Elk City 138 kV Move Load | [18 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 1778000 |  |  | 0 | 1778000 | 2037000 | 2037000 | 0% | 0% | 1200324.32 | 1200324.32 | 1200324.32 | -41.07% | 69.7% | 1176180.46 | 1176180.46 |  |  | -2.011% | 0% | Only included FERC T work, not Distribution; used cost estimate from the Capital Program Approval Improvement Requisition.
| P.026 | 2018-12-21 | Fort Towson-Valliant Line Rebuild | [18 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 1044000 |  |  | 27999.49 | 1044000 | 557000 | 557000 | 0% | 3629% | 302079.67 | 302079.67 | 302079.67 | -45.77% | 84.39% | 288859.6 | 288859.6 |  |  | -4.376% | 0% | ROW only; refer to related OKTCo project, OKT.019, P15204002/005.
| P.027 | 2018-05-04 | Duncan-Comanche Tap 69 kV Rebuild and Duncan station upgrades | [18 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 1216000 |  |  | 0 | 1216000 | 1216000 | 1216000 | 0% | 0% | 1344938.51 | 1344938.51 | 1344938.51 | 10.6% | -9.587% | 1345382.62 | 1345382.62 |  |  | 0.03302% | 0% | Refer to related OKTCo project, OKT.020. Only upgrades at Duncan Station are included here.
| P.028 | 2019-12-01 | Tulsa Southeast-E.61st 138 kV Rebuild | [26 empty] | --- | --- | --- | --- |  |  | --- | --- | 1039000 | 5024000 |  |  | --- | 7022000 | 7156000 | 0% | 0% | 6388895.58 | 7661895.58 |  |  | -9.016% | 19.93% | Includes line, ROW, and station work.
| P.029 | 2019-03-19 | Broken Arrow North-Lynn Lane East 138 kV | [26 empty] | --- | --- | --- | --- |  |  | --- | --- | 2318000 | 4120000 |  |  | --- | 4236000 | 4236000 | 0% | 0% | 5058521.96 | 5058521.96 |  |  | 19.42% | 0% | Includes reconductor and ROW.
New | P.030 | 2020-06-01 | Keystone Dam - Wekiwa 138 kV | [26 empty] | --- | --- | --- | --- |  |  | --- | --- | --- | --- |  |  | --- | 971000 | 1677000 | 0% | 0% | --- | 2842000 |  |  | 0% |  | Includes Wekiwa station work, see Transco for line work, ROW and TFC. Note, duing this update, ROW was forecast on PSO, instead of OKT. (Manually moved the ROW to OKT.)
NOTES:
< | Not above SPP $100,000 BP threshold.
New | New to BP list
c | AEP project component (components sum up to project total)
t | AEP project total
n/a | informational only; not included in calculations
Matched Last Year
Does Not Match Last Year, Needs Updating
Changed from Last Year, Updated

## SWEPCO
Code | FR Sheet Name (WS F&G) | Projected / Actual In-Service (mmm-yyyy) | Project & TP# | --- PREVIOUSLY PUBLISHED --- | [17 empty] | --- P R E V I O S L Y P U B L I S H E D --- |  |  |  | --- P R E V I O S L Y P U B L I S H E D --- |  |  |  | --- P R E V I O S L Y P U B L I S H E D --- | [5 empty] | --- P R E V I O S L Y P U B L I S H E D --- | [5 empty] | --- P R E V I O S L Y P U B L I S H E D --- |  |  |  |  | --- WS-F and WS-G SUMMARY Input Data --- | [5 empty] | COMMENTS
|  |  |  | 09 Update | 2010 "Corrected" Update |  |  | 2011 "Corrected" Update |  |  | 2012 Update |  |  | 2013 Update |  |  |  | 2014 Update |  |  |  | 2015 Update |  |  |  | 2016 Update |  |  |  | 2017 Update | [5 empty] | 2018 Update | [5 empty] | 2019 Update |  |  |  |  | 2020 Update
|  |  |  | YE2009 Projected (8/31/09) << WS-F >> | YE2009 Actual (3/29/11)* << WS-G >> | YE2010 Projected (3/29/11) << WS-F >> | YE09 to YE10 Variance | YE2010 Actual (12/21/11)* << WS-G >> | YE2011 Projected (12/21/11) << WS-F >> | YE10 to YE11 (Projected) Variance | YE2011 Actual (May'12) << WS-G >> | YE2012 Projected (May '12) << WS-F >> | YE11 to YE12 (Projected) Variance | YE2012 Actual (May'13) << WS-G >> | YE2013 Projected (May '13) << WS-F >> | YE2012 Variance (Projected to Actual) | YE12 (actual) to YE13 (Projected) Variance | YE2013 Actual (May'14) << WS-G >> | YE2014 Projected (May '14) << WS-F >> | YE2013 Variance (Projected to Actual) | YE13 (actual) to YE14 (Projected) Variance | YE2014 Actual (May'15) << WS-G >> | YE2015 Projected (May '15) << WS-F >> | YE2014 Variance (Projected to Actual) | YE14 (actual) to YE15 (Projected) Variance | YE2015 Actual (May'16) << WS-G >> | YE2016 Projected (May '16) << WS-F >> | YE2015 Variance (Projected to Actual) | YE15 (actual) to YE16 (Projected) Variance | YE2016 Actual (May'17) << WS-G >> | YE2017 Projected (May '17) << WS-F >> | YE2017 Projected Adjusted (Oct '17) << WS-F >> | YE2018 Projected (Oct '17) << WS-F >> | YE2016 Variance (Projected to Actual) | YE16 (actual) to YE17 (Projected) Variance | YE2017 Actual (May '18) << WS-G >> | YE2018 Projected (May '18) << WS-F >> | YE2018 Projected Adjusted (Oct '18) << WS-F >> | YE2019 Projected (Oct '18) << WS-F >> | YE2017 Variance (Projected to Actual) | YE17 (Actual) to YE18 (Projected) Variance | YE2018 Actual (May '19) << WS-G >> | YE2019 Projected (Oct '19) << WS-F >> | YE2020 Projected (Oct '19) << WS-F >> | YE2018 Variance (Projected to Actual) | YE18 (Actual) to YE19 (Projected) Variance | YE2019 Actual (May '20) << WS-G >> | YE2020 Projected (May '2020) << WS-F >> | YE2020 Projected (Oct '20) << WS-F >> | YE2021 Projected (Oct '20) << WS-F >> | YE2019 Variance (Projected to Actual) | YE19 (Actual) to YE20 (Projected) Variance
| S.001 | 2009-12-01 | AH auto & line (TP2007057) | 9057179 | 12134740.73 | 17740954.73 | 95.88% | 17671482 | 17671482 | 0.3931% | 17671482 | 17671482 | 0% | 17671482 | 17671482 | 0% | 0% | 17671482 | 17671482 | 0% | 0% | 17671482 | 17671482 | 0% | 0% | 17671482 | 17671482 | 0% | 0% | 17671482 | 17671482 | 17671482 | 17671482 | 0% | 0% | 17671482 | 17671482 | 17671482 | 17671482 | 0% | 0% | 17671482 | 17671482 | 17671482 | 0% | 0% | 17671482 | 17671482 |  |  | 0% | 0%
| S.002 | 2009-01-01 | SW Shreveport (TP2007060) | 11979500 | 8402687.48 | 8402687.48 | -29.86% | 8402687.48 | 8402687.48 | 0% | 8402687.48 | 8402687.48 | 0% | 8402687.48 | 8402687.48 | 0% | 0% | 8402687.48 | 8402687.48 | 0% | 0% | 8402687.48 | 8402687.48 | 0% | 0% | 8402687 | 8402687 | -5.712e-06% | 0% | 8402687 | 8402687 | 8402687 | 8402687 | -5.712e-06% | 0% | 8402687 | 8402687 | 8402687 | 8402687 | 0% | 0% | 8402687 | 8402687 | 8402687 | 0% | 0% | 8402687 | 8402687 |  |  | 0% | 0%
| S.003 | 2009-06-01 | NW Ark 2009 (TP2007103) | 13558697 | 12384562 | 14833730 | 9.404% | 13742803 | 13742803 | 7.938% | 13742803 | 13742803 | 0% | 13742803 | 13742803 | 0% | 0% | 13742803 | 13742803 | 0% | 0% | 13742803 | 13742803 | 0% | 0% | 13742804 | 13742804 | 7.277e-06% | 0% | 13742804 | 13742804 | 13742804 | 13742804 | 7.277e-06% | 0% | 13742804 | 13742804 | 13742804 | 13742804 | 0% | 0% | 13742804 | 13742804 | 13742804 | 0% | 0% | 13742804 | 13742804 |  |  | 0% | 0%
| S.004 | 2009-06-01 | N-Mag-Danville (TP2007114) | 5012222 | 11580312.94 | 11580312.94 | 131% | 11580312.94 | 11580312.94 | 0% | 11580312.94 | 11580312.94 | 0% | 11580312.94 | 11580312.94 | 0% | 0% | 11580312.94 | 11580312.94 | 0% | 0% | 11580312.94 | 11580312.94 | 0% | 0% | 11580311 | 11580311 | -1.675e-05% | 0% | 11580311 | 11580311 | 11580311 | 11580311 | -1.675e-05% | 0% | 11580311 | 11580311 | 11580311 | 11580311 | 0% | 0% | 11580311 | 11580311 | 11580311 | 0% | 0% | 11580311 | 11580311 |  |  | 0% | 0%
| S.005 | 2009-12-01 | Greenwod, AR area (TP2007120) | 2111061 | 2981232 | 2981232 | 41.22% | 2981232 | 2981232 | 0% | 2981232 | 2981232 | 0% | 2981232 | 2981232 | 0% | 0% | 2981232 | 2981232 | 0% | 0% | 2981232 | 2981232 | 0% | 0% | 2981768 | 2981768 | 0.01798% | 0% | 2981768 | 2981768 | 2981768 | 2981768 | 0.01798% | 0% | 2981768 | 2981768 | 2981768 | 2981768 | 0% | 0% | 2981768 | 2981768 | 2981768 | 0% | 0% | 2981768 | 2981768 |  |  | 0% | 0% | slight discrepancy in sum of costs versus prior total
| S.006 | 2009-06-01 | Port Robson - Caplis - Red Point (SE 138 loop) (TP2007165) | 17101764 | 5339018.68 | 6524013.68 | -61.85% | 5997609 | 27373809 | -76.17% | 20890772 | 32463272 | -15.68% | 29567877 | 34986877 | 8.015% | 18.33% | 36928458 | 36928458 | 5.549% | 0% | 37028625 | 37028625 | 0.2712% | 0% | 37028625 | 37028625 | 0% | 0% | 37028625 | 37028625 | 37028625 | 37028625 | 0% | 0% | 37028625 | 37028625 | 37028625 | 37028625 | 0% | 0% | 37028625 | 37028625 | 37028625 | 0% | 0% | 37028625 | 37028625 |  |  | 0% | 0% | Multi-element multi-year base plan project. Final in-service yr from '09 to '13.
| S.007 | 2009-05-01 | Linwood 1238 switch r&r (TP2008080) | 64397 | 64769 | 82956 | 28.82% | 77750 | 77750 | 6.696% | 77750 | 77750 | 0% | 77750 | 77750 | 0% | 0% | 77750 | 77750 | 0% | 0% | 77750 | 77750 | 0% | 0% | 77750 | 77750 | 0% | 0% | 77750 | 77750 | 77750 | 77750 | 0% | 0% | 77750 | 77750 | 77750 | 77750 | 0% | 0% | 77750 | 77750 | 77750 | 0% | 0% | 77750 | 77750 |  |  | 0% | 0% | Not over $100K threshold for regional allocation.
| S.008 | 2008-07-01 | Dyess-S.Fayetteville 69 convert to 161 (TP2002085) | 6374367 | 6406782 | 6406782 | 0.5085% | 9655697 | 9655697 | -33.65% | 9655697 | 9655697 | 0% | 9655697 | 9655697 | 0% | 0% | 9655697 | 9655697 | 0% | 0% | 9655697 | 9655697 | 0% | 0% | 9655697 | 9655697 | 0% | 0% | 9655697 | 9655697 | 9655697 | 9655697 | 0% | 0% | 9655697 | 9655697 | 9655697 | 9655697 | 0% | 0% | 9655697 | 9655697 | 9655697 | 0% | 0% | 9655697 | 9655697 |  |  | 0% | 0%
| S.009 | 2008-04-01 | NW Texkna-Bann-Alumax 138 reconductor (TP2006130) | 1864928 | 1863106 | 1863106 | -0.0977% | 2820378 | 2820378 | -33.94% | 2820378 | 2820378 | 0% | 2820378 | 2820378 | 0% | 0% | 2820378 | 2820378 | 0% | 0% | 2820378 | 2820378 | 0% | 0% | 2820328 | 2820328 | -0.001773% | 0% | 2820328 | 2820328 | 2820328 | 2820328 | -0.001773% | 0% | 2820328 | 2820328 | 2820328 | 2820328 | 0% | 0% | 2820328 | 2820328 | 2820328 | 0% | 0% | 2820328 | 2820328 |  |  | 0% | 0% | slight discrepancy in sum of costs versus prior total
| S.010 | 2008-11-01 | Tontitown-Elm Springs REC 161 | [22 empty] | 0% |  |  |  | 0% | [22 empty] | Delete: Not a BPU…no longer reported for Sched 11 purposes. Confirmed 1/19/15.
| S.011 | 2007-05-01 | Siloam Sprgs - Chamber Sprgs 161 line | [22 empty] | 0% |  |  |  | 0% | [22 empty] | Delete: Not a BPU…no longer reported for Sched 11 purposes. Confirmed 1/19/15.
| S.012 | 2007-07-01 | Knox Lee - Oak Hill#2 1328 line, S.Shreveport (TP2004036) | 124047 | 124047 | 124047 | 0% | 185247 | 185247 | -33.04% | 185247 | 185247 | 0% | 185247 | 185247 | 0% | 0% | 185247 | 185247 | 0% | 0% | 185247 | 185247 | 0% | 0% | 185247 | 185247 | 0% | 0% | 185247 | 185247 | 185247 | 185247 | 0% | 0% | 185247 | 185247 | 185247 | 185247 | 0% | 0% | 185247 | 185247 | 185247 | 0% | 0% | 185247 | 185247 |  |  | 0% | 0%
| S.013 | 2006-04-01 | Carthage REC - Carthage T 138 (TP2004139) | 3884542 | 3884542 | 3884542 | 0% | 3884542 | 3884542 | 0% | 3884542 | 3884542 | 0% | 3884542 | 3884542 | 0% | 0% | 3884542 | 3884542 | 0% | 0% | 5731607 | 5731607 | 47.55% | 0% | 5731607 | 5731607 | 0% | 0% | 5731607 | 5731607 | 5731607 | 5731607 | 0% | 0% | 5731607 | 5731607 | 5731607 | 5731607 | 0% | 0% | 5731607 | 5731607 | 5731607 | 0% | 0% | 5731607 | 5731607 |  |  | 0% | 0% | Corrected total; Shadow work order was missing from prior reports. New total correlates with orginal estimate.
| S.014 | 2007-06-01 | NW Henderson - Oak Hill 138 line (TP2006089) | 54301 | 54301 | 54301 | 0% | 81701 | 81701 | -33.54% | 81701 | 81701 | 0% | 81701 | 81701 | 0% | 0% | 81701 | 81701 | 0% | 0% | 81701 | 81701 | 0% | 0% | 81701 | 81701 | 0% | 0% | 81701 | 81701 | 81701 | 81701 | 0% | 0% | 81701 | 81701 | 81701 | 81701 | 0% | 0% | 81701 | 81701 | 81701 | 0% | 0% | 81701 | 81701 |  |  | 0% | 0% | Not over $100K threshold for regional allocation.
| S.015 | 2007-07-01 | Arsenal Hill 138 kV cap (TP2004148) | 247950 | 247950 | 247950 | 0% | 372149 | 372149 | -33.37% | 372149 | 372149 | 0% | 372149 | 372149 | 0% | 0% | 372149 | 372149 | 0% | 0% | 372149 | 372149 | 0% | 0% | 372149 | 372149 | 0% | 0% | 372149 | 372149 | 372149 | 372149 | 0% | 0% | 372149 | 372149 | 372149 | 372149 | 0% | 0% | 372149 | 372149 | 372149 | 0% | 0% | 372149 | 372149 |  |  | 0% | 0%
| S.016 | 2008-12-01 | Daingerfield repl CB 1M90 (TP2008017) | ** | 0 | 310667 | n/a | 389326 | 389326 | -20.2% | 389326 | 389326 | 0% | 389326 | 389326 | 0% | 0% | 389326 | 389326 | 0% | 0% | 389326 | 389326 | 0% | 0% | 389326 | 389326 | 0% | 0% | 389326 | 389326 | 389326 | 389326 | 0% | 0% | 389326 | 389326 | 389326 | 389326 | 0% | 0% | 389326 | 389326 | 389326 | 0% | 0% | 389326 | 389326 |  |  | 0% | 0%
| S.017 | 2008-06-01 | Linwood-McWillie (TP2007019) | 1300389 | 1949836.51 | 1949836.51 | 49.94% | 1949836.51 | 1949836.51 | 0% | 1949836.51 | 1949836.51 | 0% | 1949836.51 | 1949836.51 | 0% | 0% | 1949836.51 | 1949836.51 | 0% | 0% | 1949836.51 | 1949836.51 | 0% | 0% | 1949836.51 | 1949836.51 | 0% | 0% | 1949836.51 | 1949836.51 | 1949836.51 | 1949836.51 | 0% | 0% | 1949836.51 | 1949836.51 | 1949836.51 | 1949836.51 | 0% | 0% | 1949836.51 | 1949836.51 | 1949836.51 | 0% | 0% | 1949836.51 | 1949836.51 |  |  | 0% | 0%
| S.018 | 2008-10-01 | Port Robson - Caplis (SE 1238 kV loop - 2008) (TP2007165) | *** | n/a | n/a | n/a | --- | --- | --- | --- | --- |  | --- | --- | n/a | n/a | [8 empty] | 0% |  |  |  | 0% | [22 empty] | Delete duplicate project. Will track this multi-element multi-year project via 1 set of worksheet F and G tables.
| S.019 | 2008-05-01 | Wallace Lake - Port Robson (TP2005142) | 2811966 | 4480167.62 | 4480167.62 | 59.33% | 4480167.62 | 4480167.62 | 0% | 4480167.62 | 4480167.62 | 0% | 4480167.62 | 4480167.62 | 0% | 0% | 4480167.62 | 4480167.62 | 0% | 0% | 4480167.62 | 4480167.62 | 0% | 0% | 4480168 | 4480168 | 8.482e-06% | 0% | 4480168 | 4480168 | 4480168 | 4480168 | 8.482e-06% | 0% | 4480168 | 4480168 | 4480168 | 4480168 | 0% | 0% | 4480168 | 4480168 | 4480168 | 0% | 0% | 4480168 | 4480168 |  |  | 0% | 0%
| S.020 | 2008-11-01 | [NW Ark Area Improve - 2008] Elm Springs, East Rogers,Shipe Rd stations | 1165466 | 1165466 | 1165466 | 0% | --- | --- | --- | --- | --- |  | --- | --- | n/a | n/a | [8 empty] | 0 |  |  |  | 0 | [22 empty] | Transfer: Will track this multi-element multi-year project via S.003 from 2011 Update forward. Investment now included in S.003 above.
| S.021 | 2010-06-01 | McNabb-Turk 4mi reconductor | n/a | 837610 | 2389000 | n/a | 1609803 | 1609803 | 48.4% | 1638972 | 1638972 | -1.78% | 1638972 | 1638972 | 0% | 0% | 1638972 | 1638972 | 0% | 0% | 1642817 | 1642817 | 0.2346% | 0% | 1642817 | 1642817 | 0% | 0% | 1642817 | 1642817 | 1642817 | 1642817 | 0% | 0% | 1642817 | 1642817 | 1642817 | 1642817 | 0% | 0% | 1642817 | 1642817 | 1642817 | 0% | 0% | 1642817 | 1642817 |  |  | 0% | 0% | Corrected total.
| S.022 | 2010-06-01 | Longwood: r&r switches & bus upgrade | n/a | 0 | 187900 | n/a | 215000 | 215000 | -12.6% | 205882 | 205882 | 4.429% | 205882 | 205882 | 0% | 0% | 205882 | 205882 | 0% | 0% | 205882 | 205882 | 0% | 0% | 205882 | 205882 | 0% | 0% | 205882 | 205882 | 205882 | 205882 | 0% | 0% | 205882 | 205882 | 205882 | 205882 | 0% | 0% | 205882 | 205882 | 205882 | 0% | 0% | 205882 | 205882 |  |  | 0% | 0%
| S.023 | 2010-06-01 | Reconductor: Greggton-Lake Lamond & Quitman-Westwood 69 kV lines (TP2008015) | n/a | 0 | 4839000 | n/a | 4795139 | 4795139 | 0.9147% | 4795139 | 4795139 | 0% | 4795139 | 4795139 | 0% | 0% | 4795139 | 4795139 | 0% | 0% | 4795139 | 4795139 | 0% | 0% | 4795139 | 4795139 | 0% | 0% | 4795139 | 4795139 | 4795139 | 4795139 | 0% | 0% | 4795139 | 4795139 | 4795139 | 4795139 | 0% | 0% | 4795139 | 4795139 | 4795139 | 0% | 0% | 4795139 | 4795139 |  |  | 0% | 0%
| S.024 | 2010-06-01 | Rebuild/recondutor Dyess-ElmSprings REC [Dyess Station-Flint Creek] (TP2008026) | n/a | 0 | 5473000 | n/a | 5250739 | 5250739 | 4.233% | 5250739 | 5250739 | 0% | 5250739 | 5250739 | 0% | 0% | 5250739 | 5250739 | 0% | 0% | 5250739 | 5250739 | 0% | 0% | 5250739 | 5250739 | 0% | 0% | 5250739 | 5250739 | 5250739 | 5250739 | 0% | 0% | 5250739 | 5250739 | 5250739 | 5250739 | 0% | 0% | 5250739 | 5250739 | 5250739 | 0% | 0% | 5250739 | 5250739 |  |  | 0% | 0%
| S.025 | 2010-12-01 | Replace sw @ Diana | n/a | 0 | 91500 | n/a | 88842 | 88842 | 2.992% | 88842 | 88842 | 0% | 88842 | 88842 | 0% | 0% | 88842 | 88842 | 0% | 0% | 88842 | 88842 | 0% | 0% | 88842 | 88842 | 0% | 0% | 88842 | 88842 | 88842 | 88842 | 0% | 0% | 88842 | 88842 | 88842 | 88842 | 0% | 0% | 88842 | 88842 | 88842 | 0% | 0% | 88842 | 88842 |  |  | 0% | 0% | Not over $100K threshold for regional allocation.
| S.026 | 2011-06-01 | Whitney repl CB and Switches | --- | --- | --- | --- | --- | 279600 | n/a | 249141 | 249141 | 12.23% | 249141 | 249141 | 0% | 0% | 249141 | 249141 | 0% | 0% | 249141 | 249141 | 0% | 0% | 249141 | 249141 | 0% | 0% | 249141 | 249141 | 249141 | 249141 | 0% | 0% | 249141 | 249141 | 249141 | 249141 | 0% | 0% | 249141 | 249141 | 249141 | 0% | 0% | 249141 | 249141 |  |  | 0% | 0%
| S.027 | 2012-06-01 | Linwood - Powell Street 138 kV | --- | --- | --- | --- | --- | --- | n/a | --- | 450200 | n/a | 430017 | 430017 | -4.483% | 0% | 430017 | 430017 | 0% | 0% | 421517 | 421517 | -1.977% | 0% | 421517 | 421517 | 0% | 0% | 421517 | 421517 | 421517 | 421517 | 0% | 0% | 421517 | 421517 | 421517 | 421517 | 0% | 0% | 421517 | 421517 | 421517 | 0% | 0% | 421517 | 421517 |  |  | 0% | 0% | Corrected total (took out removal cost)
| S.028 | 2012-06-01 | Bloomburg-Texarkana Plant (TP2008027) | --- | --- | --- | --- | --- | --- | n/a | --- | 5819300 | n/a | 5267709 | 5267709 | -9.479% | 0% | 5268487 | 5268487 | 0.01477% | 0% | 5268487 | 5268487 | 0% | 0% | 5268479 | 5268479 | -0.0001518% | 0% | 5268479 | 5268479 | 5268479 | 5268479 | -0.0001518% | 0% | 5268479 | 5268479 | 5268479 | 5268479 | 0% | 0% | 5268479 | 5268479 | 5268479 | 0% | 0% | 5268479 | 5268479 |  |  | 0% | 0% | slight discrepancy in sum of costs versus prior total
| S.029 | 2012-12-01 | Knox Lee - Pirkey 138 kV / Pirkey - Whitney 138 kV - Replace Breaker, Wavetraps, and reset relays and CT's (TP2010062) | --- | --- | --- | --- | --- | --- | n/a | --- | 1521900 | n/a | 1886753 | 1886753 | 23.97% | 0% | 1881887 | 1881887 | -0.2579% | 0% | 1881887 | 1881887 | 0% | 0% | 1881887 | 1881887 | 0% | 0% | 1881887 | 1881887 | 1881887 | 1881887 | 0% | 0% | 1881887 | 1881887 | 1881887 | 1881887 | 0% | 0% | 1881887 | 1881887 | 1881887 | 0% | 0% | 1881887 | 1881887 |  |  | 0% | 0%
| S.030 | 2012-08-31 | NW Texarkana - Turk 345 | --- | --- | --- | --- | --- | --- | n/a | --- | 47434000 | n/a | 47172572 | 47172572 | -0.5511% | 0% | 47415121 | 47415121 | 0.5142% | 0% | 47659752 | 47659900 | 0.5159% | 0.0003105% | #REF! | 47659900 | #REF! | #REF! | 47660028.54 | 47660028.54 | 47660028.54 | 47660028.54 | 0.0002697% | 0% | 47660028.54 | 47660028.54 | 47660028.54 | 47660028.54 | 0% | 0% | 47660028.54 | 47660028.54 | 47660028.54 | 0% | 0% | 47660028.54 | 47660028.54 |  |  | 0% | 0%
| S.031 | 2012-06-01 | Lone Star South - Pittsburg 138 kV - Replace Wavetraps, reset CT's and Relays (TP2009100) | --- | --- | --- | --- | --- | --- | n/a | --- | 284100 | n/a | 230750 | 230750 | -18.78% | 0% | 230750 | 230750 | 0% | 0% | 230750 | 230750 | 0% | 0% | 230750 | 230750 | 0% | 0% | 230750 | 230750 | 230750 | 230750 | 0% | 0% | 230750 | 230750 | 230750 | 230750 | 0% | 0% | 230750 | 230750 | 230750 | 0% | 0% | 230750 | 230750 |  |  | 0% | 0%
| S.032 | 2012-06-01 | Howell-Kilgore 69 kV rebuild | --- | --- | --- | --- | --- | --- | n/a | --- | 3985900 | n/a | 4204655 | 4204655 | 5.488% | 0% | 4157737 | 4157737 | -1.116% | 0% | 4175110 | 4175110 | 0.4178% | 0% | 4175110 | 4175110 | 0% | 0% | 4175110 | 4175110 | 4175110 | 4175110 | 0% | 0% | 4175110 | 4175110 | 4175110 | 4175110 | 0% | 0% | 4175110 | 4175110 | 4175110 | 0% | 0% | 4175110 | 4175110 |  |  | 0% | 0%
| S.033 | 2014-04-01 | Flint Creek-Shipe Road 345 kV Line (TP2008126) | --- | --- | --- | --- | --- | --- | n/a | --- | 1609000 | n/a | 4101857 | 12471857 | 154.9% | 204.1% | 8981434 | 55496134 | -27.99% | 517.9% | 58065903 | 57951403 | 4.631% | -0.1972% | 58124321.73 | 59295600.19 | 0.2984% | 2.015% | 59305787.9 | 59305787.9 | 59305787.9 | 59305787.9 | 0.01718% | 0% | 59305787.9 | 59305787.9 | 59305787.9 | 59305787.9 | 0% | 0% | 59305787.9 | 59305787.9 | 59305787.9 | 0% | 0% | 59305787.9 | 59305787.9 |  |  | 0% | 0% | Multi-element multi-year base plan project. Work orginally projected for 2013 was moved to 2014. Final in-service yr in 12', 13' and 14'.
| S.034 | 2013-11-01 | Bann - LS Ordnance - Hooks 69 kV - Rebuild 7.1 mi (TP2011024) | --- | --- | --- | --- | --- | --- | n/a | --- | --- | n/a | --- | 8177700 | n/a | n/a | 8593855 | 8593855 | 5.089% | 0% | 8598828 | 8598828 | 0.05787% | 0% | 8598828 | 8598828 | 0% | 0% | 8598828 | 8598828 | 8598828 | 8598828 | 0% | 0% | 8598828 | 8598828 | 8598828 | 8598828 | 0% | 0% | 8598828 | 8598828 | 8598828 | 0% | 0% | 8598828 | 8598828 |  |  | 0% | 0%
| S.035 | 2013-06-01 | Diana - Replace North Autotransformer #3 (TP2010065) | --- | --- | --- | --- | --- | --- | n/a | --- | --- | n/a | --- | 3795000 | n/a | n/a | 4344847 | 4344847 | 14.49% | 0% | 4344850 | 4344850 | 6.905e-05% | 0% | 4344850 | 4344850 | 0% | 0% | 4344850 | 4344850 | 4344850 | 4344850 | 0% | 0% | 4344850 | 4344850 | 4344850 | 4344850 | 0% | 0% | 4344850 | 4344850 | 4344850 | 0% | 0% | 4344850 | 4344850 |  |  | 0% | 0%
| S.036 | 2013-09-01 | Osburn 161 kV Line Work | --- | --- | --- | --- | --- | --- | n/a | --- | --- | n/a | --- | 1750000 | n/a | n/a | 3038117 | 3038117 | 73.61% | 0% | 6389739 | 6389739 | 110.3% | 0% | 6389739 | 6389739 | 0% | 0% | 6389739 | 6389739 | 6389739 | 6389739 | 0% | 0% | 6389739 | 6389739 | 6389739 | 6389739 | 0% | 0% | 6389739 | 6389739 | 6389739 | 0% | 0% | 6389739 | 6389739 |  |  | 0% | 0% | Includes T station and T line per Pennybaker/Rainbolt
| S.037 | 2013-06-01 | SW Shreveport to Spring Ridge REC 138 kV Line Rebuild (TP2010066) | --- | --- | --- | --- | --- | --- | n/a | --- | --- | n/a | --- | 4585200 | n/a | n/a | 5048185 | 5048185 | 10.1% | 0% | 5048526 | 5048526 | 0.006755% | 0% | 5048526 | 5048526 | 0% | 0% | 5048526 | 5048526 | 5048526 | 5048526 | 0% | 0% | 5048526 | 5048526 | 5048526 | 5048526 | 0% | 0% | 5048526 | 5048526 | 5048526 | 0% | 0% | 5048526 | 5048526 |  |  | 0% | 0%
| S.038 | 2013-06-01 | Eastex Switching Station - Whitney 138 kV Station - Rebuild 2.5 miles of 138 kV (TP2010064) | --- | --- | --- | --- | --- | --- | n/a | --- | --- | n/a | --- | 3095000 | n/a | n/a | 2636239 | 2636239 | -14.82% | 0% | 2636239 | 2636239 | 0% | 0% | 2636239 | 2636239 | 0% | 0% | 2636239 | 2636239 | 2636239 | 2636239 | 0% | 0% | 2636239 | 2636239 | 2636239 | 2636239 | 0% | 0% | 2636239 | 2636239 | 2636239 | 0% | 0% | 2636239 | 2636239 |  |  | 0% | 0%
| S.039 | 2013-02-01 | Ashdown West - Craig Junction 138KV Rebuild (TP2009092) | [14 empty] | 4316127 | 4316127 |  |  | 4316668 | 4316668 | 0.01253% | 0% | 4316668 | 4316668 | 0% | 0% | 4316668 | 4316668 | 4316668 | 4316668 | 0% | 0% | 4316668 | 4316668 | 4316668 | 4316668 | 0% | 0% | 4316668 | 4316668 | 4316668 | 0% | 0% | 4316668 | 4316668 |  |  | 0% | 0% | Asset has been transferred to SWEPCO from PSO, thus placing the line back with the original owner.
| S.040 | 2014-06-01 | Rock Hill to Carthage 69 kV Rebuild 11.4 Miles (TP2010102) | [14 empty] | 0 | 9550200 |  |  | 9637037 | 9637037 | 0.9093% | 0% | 9637037 | 9637037 | 0% | 0% | 9637037 | 9637037 | 9637037 | 9637037 | 0% | 0% | 9637037 | 9637037 | 9637037 | 9637037 | 0% | 0% | 9637037 | 9637037 | 9637037 | 0% | 0% | 9637037 | 9637037 |  |  | 0% | 0%
| S.041 | 2014-12-01 | Broadmoor to Fern Street 69 kV Rebuild 1 mile (TP2010103) | [14 empty] | 0 | 3846600 |  |  | 4675710 | 4795000 | 21.55% | 2.551% | 4825048 | 4795000 | 0.6267% | -0.6228% | 4866028.31 | 4866028.31 | 4866028.31 | 4866028.31 | 1.481% | 0% | 4866028.31 | 4866028.31 | 4866028.31 | 4866028.31 | 0% | 0% | 4866028.31 | 4866028.31 | 4866028.31 | 0% | 0% | 4866028.31 | 4866028.31 |  |  | 0% | 0% | Includes terminal work at both Fern Street and Broadmoor.
| S.042 | 2014-06-01 | Northwest Henderson to Poynter 69 kV Rebuild 3.2 miles (TP2004031) | [14 empty] | 0 | 4520000 |  |  | 5289194 | 5289194 | 17.02% | 0% | 5289194 | 5289194 | 0% | 0% | 5289194 | 5289194 | 5289194 | 5289194 | 0% | 0% | 5289194 | 5289194 | 5289194 | 5289194 | 0% | 0% | 5289194 | 5289194 | 5289194 | 0% | 0% | 5289194 | 5289194 |  |  | 0% | 0% | Includes terminal work at both Northwest Henderson and Poynter
| S.043 | 2014-11-01 | Diana to Perdue 138 kV Rebuild 21.8 miles; Station Upgrades at Diana and Perdue (TP2011023) | [14 empty] | 0 | 14332500 |  |  | 14950466 | 15026000 | 4.312% | 0.5052% | 14866883.03 | 15026000 | -1.059% | 1.07% | 14866883.03 | 14866883.03 | 14866883.03 | 14866883.03 | -1.059% | 0% | 14866883.03 | 14866883.03 | 14866883.03 | 14866883.03 | 0% | 0% | 14866883.03 | 14866883.03 | 14866883.03 | 0% | 0% | 14866883.03 | 14866883.03 |  |  | 0% | 0%
| S.044 | 2007-11-01 | Pittsburg-Winnsboro-North Mineola | [18 empty] | 29107362.05 | 29107362.05 |  |  | 29107362.05 | 29107362.05 |  |  | 29107362.05 | 29107362.05 | 29107362.05 | 29107362.05 |  |  | 29107362.05 | 29107362.05 | 29107362.05 | 29107362.05 |  |  | 29107362.05 | 29107362.05 | 29107362.05 |  |  | 29107362.05 | 29107362.05 |  |  |  |  | not sure if stations are to be included
| S.045 | 2007-03-01 | CHAMBER SPRINGS - TONTITOWN 161KV CKT 1 | [18 empty] | 2658452 | 2658452 |  |  | 2658452 | 2658452 |  |  | 2658452 | 2658452 | 2658452 | 2658452 |  |  | 2658452 | 2658452 | 2658452 | 2658452 |  |  | 2658452 | 2658452 | 2658452 |  |  | 2658452 | 2658452
| S.046 | 2008-05-01 | CHAMBER SPRINGS - TONTITOWN 345KV CKT 1 | [18 empty] | 16318844 | 16318844 |  |  | 16318844 | 16318844 |  |  | 16318844 | 16318844 | 16318844 | 16318844 |  |  | 16318844 | 16318844 | 16318844 | 16318844 |  |  | 16318844 | 16318844 | 16318844 |  |  | 16318844 | 16318844 |  |  |  |  | Includes 345 kV line and Chamber Springs 345 kV terminal work.
| S.047 | 2012-02-01 | FULTON - HOPE 115KV CKT 1 | [18 empty] | 787880 | 787880 |  |  | 787880 | 787880 |  |  | 787880 | 787880 | 787880 | 787880 |  |  | 787880 | 787880 | 787880 | 787880 |  |  | 787880 | 787880 | 787880 |  |  | 787880 | 787880
| S.048 | 2010-03-01 | MINEOLA - NORTH MINEOLA 69KV CKT 1 | [18 empty] | 160296.1 | 160296.1 |  |  | 160296.1 | 160296.1 |  |  | 160296.1 | 160296.1 | 160296.1 | 160296.1 |  |  | 160296.1 | 160296.1 | 160296.1 | 160296.1 |  |  | 160296.1 | 160296.1 | 160296.1 |  |  | 160296.1 | 160296.1 |  |  |  |  | 69 kV Upgrade.
| S.049 |  | BANN - KINGS HIGHWAY 69KV CKT 1 | [18 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 |  |  |  |  | Ignore; Distribution investment
| S.050 |  | LONE STAR SOUTH - PITTSBURG 138KV CKT 1 | [18 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 |  |  |  |  | Ignore; no Capital investment
| S.051 |  | BANN - LONESTAR ORDINANCE TAP 69KV CKT 1 | [18 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 |  |  |  |  | Ignore; no Capital investment
| S.052 |  | FOREST HILLS REC - QUITMAN 69KV CKT 1 | [18 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 |  |  |  |  | Ignore; Distribution investment
| S.053 |  | MAGNOLIA TAP - WINNSBORO 69KV CKT 1 | [18 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 |  |  |  |  | Ignore; Distribution investment
| S.054 |  | CARTHAGE - ROCK HILL 69KV CKT 1 | [18 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 |  |  |  |  | Ignore; no Capital investment
| S.055 |  | FOREST HILLS REC - QUITMAN 69KV CKT 1 #2 | [18 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 |  |  |  |  | Ignore; no Capital investment
| S.056 | 2010-11-01 | SUGAR HILL 138/69KV TRANSFORMER CKT 1 | [18 empty] | 23215.78 | 23215.78 |  |  | 23215.78 | 23215.78 |  |  | 23215.78 | 23215.78 | 23215.78 | 23215.78 |  |  | 23215.78 | 23215.78 | 23215.78 | 23215.78 |  |  | 23215.78 | 23215.78 | 23215.78 |  |  | 23215.78 | 23215.78 |  |  |  |  | Not over $100K threshold for regional allocation.
| S.057 |  | OKAY - TOLLETTE 69KV CKT 1 | [18 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 |  |  |  |  | Ignore; no Capital investment
| S.058 | 2016-12-16 | Valliant-NW Texarkana 345 kV | [18 empty] | 0 | 4700000 |  |  | 4525574.69 | 5020278.69 | -3.711% | 10.93% | 94208721.06 | 99956721.06 | 99956721.06 | 99956721.06 | 1777% | 6.101% | 97244454.87 | 99956721.06 | 99956721.06 | 99956721.06 | -2.713% | 2.789% | 97368971.1 | 97368971.1 | 97368971.1 | -2.589% | 2.658% | 97370354 | 97370354 |  |  | 0.00142% | 0% | Northwest Texarkana 345 kV terminal work and 345 kV ine relocations completed November 2015; Also see related PSO project (P.018) and OKTCo project (OKT.009).
| S.059 | 2017-07-01 | Brownlee-North Market 69 kV Rebuild | [18 empty] | 0 | 5900000 |  |  | 0 | 9636180.69 |  |  | 606412.23 | 16078412.23 | 16078412.23 | 16078412.23 | -93.71% | 2551% | 17140808.91 | 16078412.23 | 16078412.23 | 16078412.23 | 6.608% | -6.198% | 17132431.49 | 17132431.49 | 17132431.49 | 6.555% | -6.152% | 17132604 | 17132604 |  |  | 0.001007% | 0% | Brownlee Road Station upgrades in-serviced 5/16; remainder of project to be in-serviced 6/17.
| S.060 | 2016-04-01 | Rock Hill-Springridge Pan-Harr REC 138 kV Ckt 1 | [18 empty] | 0 | 0 |  |  | 18845095.45 | 23229161.06 |  | 23.26% | 24727060.23 | 25217060.23 | 25217060.23 | 25217060.23 | 6.448% | 1.982% | 25330929.21 | 25217060.23 | 25217060.23 | 25217060.23 | 0.4516% | -0.4495% | 25330929.21 | 25217060.23 | 25217060.23 | 0.4516% | -0.4495% | 25330929.21 | 25330929.21 |  |  | 0.4516% | 0% | Includes all components in project
| S.063 | 2016-04-21 | Winnsboro 138 kV (TP2013122) | [18 empty] | 0 | 0 |  |  | 0 | 1140471.94 |  |  | 1230858.46 | 1230858.46 | 1230858.46 | 1230858.46 | 7.925% | 0% | 1231360.51 | 1230858.46 | 1230858.46 | 1230858.46 | 0.04079% | -0.04077% | 1231360.51 | 1230858.46 | 1230858.46 | 0.04079% | -0.04077% | 1231360.51 | 1231360.51 |  |  | 0.04079% | 0%
| S.082 | 2016-06-01 | Messick 500/230 kV (TP2011033) | [18 empty] | 0 | 0 |  |  | 0 | 54032914.56 |  |  | 58503883.45 | 59534283.45 | 59534283.45 | 59534283.45 | 8.275% | 1.761% | 59387255.91 | 59534283.45 | 59534283.45 | 59534283.45 | -0.247% | 0.2476% | 58648888.77 | 58648888.77 | 58648888.77 | -1.487% | 1.51% | 58649880.67 | 58649880.67 |  |  | 0.001691% | 0% | Includes all P11033 components: station, land, line connection work
| S.064 | 2016-09-10 | Logansport 138 kV (TP2011022) | [18 empty] | 0 | 0 |  |  | 0 | 1111301.77 |  |  | 1556621.42 | 1556621.42 | 1556621.42 | 1556621.42 | 40.07% | 0% | 1558180.61 | 1556621.42 | 1556621.42 | 1556621.42 | 0.1002% | -0.1001% | 1558180.61 | 1556621.42 | 1556621.42 | 0.1002% | -0.1001% | 1558180.61 | 1558180.61 |  |  | 0.1002% | 0%
| S.067 | 2015-06-05 | Dekalb-New Boston 69 kV | [18 empty] | 49364.11 | 15500000 |  |  | 15777910.71 | 15777910.71 | 1.793% | 0% | 15991916.9 | 15998916.9 | 15998916.9 | 15998916.9 | 1.356% | 0.04377% | 16142203.19 | 15998916.9 | 15998916.9 | 15998916.9 | 0.8956% | -0.8877% | 16209336.9 | 16209336.9 | 16209336.9 | 1.315% | -1.298% | 15930624.49 | 15930624.49 |  |  | -1.719% | 0% | 69 kV Upgrade. Dekalb Station upgrades in-serviced Oct-14.
| S.068 | 2016-04-13 | Ellerbe Rd - South Shreveport 69 kV Build (TP201154) | [18 empty] | 0 | 0 |  |  | 0 | 8831593.04 |  |  | 9375483.42 | 9375483.42 | 9375483.42 | 9375483.42 | 6.158% | 0% | #REF! | 9375483.42 | 9375483.42 | 9375483.42 | #REF! | #REF! | #REF! | 9375483.42 | 9375483.42 | #REF! | #REF! | #REF! | 9381462.72 |  |  | #REF! | #REF!
| S.069 | 2015-06-25 | Hardy Street-Waterworks 69 kV | [18 empty] | 0 | 5200000 |  |  | 5366606.14 | 5366606.14 | 3.204% | 0% | 5401890.07 | 5429685.07 | 5429685.07 | 5429685.07 | 0.6575% | 0.5145% | 5522411.15 | 5429685.07 | 5429685.07 | 5429685.07 | 1.708% | -1.679% | 5522411.15 | 5522411.15 | 5522411.15 | 1.708% | -1.679% | 5522411.15 | 5522411.15 |  |  | 0% | 0% | 69 kV Upgrade.
| S.070 | 2015-05-15 | Red Oak (State Line)-North Huntington 69 kV | [18 empty] | 3741684.51 | 12300000 |  |  | 11990487.31 | 11990487.31 | -2.516% | 0% | 12017566.6 | 12017566.6 | 12017566.6 | 12017566.6 | 0.2258% | 0% | 12017566.6 | 12017566.6 | 12017566.6 | 12017566.6 | 0% | 0% | 12017566.6 | 12017566.6 | 12017566.6 | 0% | 0% | 12017566.6 | 12017566.6 |  |  | 0% | 0% | 69 kV Upgrade. State Line to Midland line rebuild in-serviced Dec-14.
| S.071 | 2015-05-01 | Mt. Pleasant - West Mt. Pleasant 69 kV Ckt 1 | [18 empty] | 0 | 5900000 |  |  | 5724549.21 | 5724549.21 | -2.974% | 0% | 5738012.91 | 5738012.91 | 5738012.91 | 5738012.91 | 0.2352% | 0% | 5738012.91 | 5738012.91 | 5738012.91 | 5738012.91 | 0% | 0% | 5738012.91 | 5738012.91 | 5738012.91 | 0% | 0% | 5738012.91 | 5738012.91 |  |  | 0% | 0% | 69 kV Upgrade.
| S.072 | 2015-11-01 | Benteler - Port Robson 138 kV Ckt 1 and 2 | [18 empty] | #REF! | 13860000 |  |  | #REF! | 13875791.7 | #REF! | #REF! | 13851900 | 13851900 | 13851900 | 13851900 | -0.1722% | 0% | 13851900 | 13851900 | 13851900 | 13851900 | 0% | 0% | 13851900 | 13851900 | 13851900 | 0% | 0% | 13851900 | 13851900 |  |  | 0% | 0%
| S.073 | 2017-06-26 | Letourneau 69 kV Capacitor Bank Addition | [18 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 1185000 | 1185000 | 1185000 |  |  | 1244156.8 | 1185000 | 1185000 | 1185000 | 4.992% | -4.755% | 1247291.61 | 1247291.61 | 1247291.61 | 5.257% | -4.994% | 1247291.61 | 1247291.61 |  |  | 0% | 0%
| S.074 | 2017-12-20 | Brooks Street - Edwards Street 69 kV Line Rebuild | [18 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 5508000 | 5508000 | 5508000 |  |  | 3816677.16 | 5508000 | 5508000 | 5508000 | -30.71% | 44.31% | 4649535.7 | 4649535.7 | 4649535.7 | -15.59% | 18.46% | 4648771.29 | 4648771.29 |  |  | -0.01644% | 0% | Includes line, ROW, and terminal upgrades. ISD moved out to 2018. Station components were moved to rehab, P14138004 and P14138005 (P14138006/007 are shadows - these two were not included last year) are under TA2015706.
| S.075 | 2017-04-01 | Hallsville - Marshall New 69 kV Circuit | [18 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 12938000 | 15870000 | 15870000 |  |  | 17094285.41 | 15870000 | 15870000 | 15870000 | 7.714% | -7.162% | 17159057.35 | 17159057.35 | 17159057.35 | 8.123% | -7.512% | 17159057.35 | 17159057.35 |  |  | 0% | 0% | Includes line, ROW, and Marshall terminal upgrades. BPIDs P13167004, 005, 006, 009, 010, 014 and shadow BPIDs.
| S.076 | 2017-11-09 | Daingerfield - Jenkins Rebuild | [18 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 1835000 | 1835000 | 1835000 |  |  | 2368917.22 | 1835000 | 1835000 | 1835000 | 29.1% | -22.54% | 2385215.9 | 2385215.9 | 2385215.9 | 29.98% | -23.07% | 2385215.9 | 2385215.9 |  |  | 0% | 0% | Includes line and ROW.
| S.077 | 2017-07-01 | Broadmoor - Fort Humbug 69 kV Rebuild | [18 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 6425000 | 6425000 | 6425000 |  |  | 6480399.04 | 6425000 | 6425000 | 6425000 | 0.8622% | -0.8549% | 6505905.04 | 6505905.04 | 6505905.04 | 1.259% | -1.244% | 6516183.71 | 6516183.71 |  |  | 0.158% | 0% | Includes line and terminal upgrades. Project is in service in 2017.
| S.078 | 2017-03-28 | Chamber Springs - Farmington 161 kV Line | [18 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 554275 | 9206275 | 9206275 | 9206275 |  |  | 10563889.59 | 9206275 | 9206275 | 9206275 | 14.75% | -12.85% | 10670271.15 | 10670271.15 | 10670271.15 | 15.9% | -13.72% | 10668801.15 | 10668801.15 |  |  | -0.01378% | 0%
| S.061 | 2018-05-11 | Evenside - Northwest Henderson 69 kV Line Rebuild | [18 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 9731000 |  |  | 0 | 9731000 | 9731000 | 9731000 | 0% | 0% | 11168314.8 | 11168314.8 | 11168314.8 | 14.77% | -12.87% | 11171456.22 | 11171456.22 |  |  | 0.02813% | 0%
| S.079 | 2017-04-01 | Hallsville - Longview Heights 69 kV Line Rebuild | [18 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 9152000 |  |  | 0 | 9152000 | 9152000 | 9152000 | 0% | 0% | 9930039.32 | 9930039.32 | 9930039.32 | 8.501% | -7.835% | 9930039.32 | 9930039.32 |  |  | 0% | 0% | includes line, ROW, and Longview Hgts terminal upgrades. BPIDs P13167001, 002, 003 and shadow BPIDs.
| S.080 | 2018-05-10 | Linwood - South Shreveport 138 kV Line Rebuild | [18 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 7885000 |  |  | 0 | 7885000 | 7885000 | 7885000 | 0% | 0% | 7195411.25 | 7195411.25 | 7195411.25 | -8.746% | 9.584% | 7196364.36 | 7196364.36 |  |  | 0.01325% | 0% | Includes line and ROW, and terminal work at Linwood and South Shreveport. Station work was done under TA2015706 (P14139003/004/503/504)
| S.081 | 2018-12-13 | IPC 138 kV Capacitor Bank Addition | [18 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 1254000 |  |  | 0 | 1254000 | 1641000 | 1690000 | 0% | 0% | 1689644.66 | 1689644.66 | 1689644.66 | 2.964% | 0.02103% | 1742923.97 | 1742923.97 |  |  | 3.153% | 0%
| S.082 | 2019-03-01 | Ellerbe Road - Lucas 69 kV Rebuild | [26 empty] | --- | --- | --- | --- |  |  | --- | --- | 6282000 | 7957000 |  |  | --- | 7957000 | 7957000 | 0% | 0% | #REF! | 9626252.49 |  |  | 0% | #REF!
| S.083 | 2019-06-01 | Siloam Springs - Siloam Springs City 161 kV Rebuild | [26 empty] | --- | --- | --- | --- |  |  | --- | --- | 661000 | 3858000 |  |  | --- | 3858000 | 3858000 | 0% | 0% | 3813966.16 | 3813966.16 |  |  | -1.141% | 0% | Includes line, ROW, and terminal work at Siloam Springs.
New | S.084 | 2019-04-11 | Figure Five - VBI North 69 kV Rebuild | [26 empty] | --- | --- | --- | --- |  |  | --- | --- | --- | --- |  |  | --- | 1951000 | 1951000 | 0% | 0% | 2910918 | 2910918 |  |  | 49.2% | 0% | A16806004 (A16806504 Shadow) is the line (43% of this BPID, as it includes more than the NTC), and A16806008 (A16806508) is the ROW (10% of this BPID, as it includes more than the NTC), located in the SWEPCo Line Rehab program. Project was not included last year b/c NTC was received after the update, so PIS data was used to get the cost for this project, as it went in-service in 2019.
NOTES:
< | Not above SPP $100,000 BP threshold.
New | New to BP list
c | AEP project component (components sum up to project total)
t | AEP project total
n/a | informational only; not included in calculations
Matched Last Year
Does Not Match Last Year, Needs Updating
Changed from Last Year, Updated